## Sheet1
Goal: Complete JavaScript Course 2022
|  | Project Title | Course on Udemy |  | Project Duration | 7/17/22 to 7/31/22
|  | Project Manager | Olga Timbur |  | Time | 56h
WBS Number | Task Title | Task Owner | Budget | Start Date | Due Date | Duration | Resources/Notes
1 | Define the class on Udemy | Olga Timbur | 28 | 2022-07-17 | 2022-07-07 | One day | https://www.udemy.com/
2 | Materials | Olga Timbur | 8 | 2022-07-17 | 2022-07-17 | 2 h | Materials are purchased
2.1 | Computer | Olga Timbur | 0 | 2022-07-17 | 2022-07-17 | 1h | Check if computer is functioning propretly.
2.2 | Second Monitor | Olga Timbur | 0 | 2022-07-17 | 2022-07-17 | N/A | Completed
2.3 | Notebook | Olga Timbur | 5 | 2022-07-17 | 2022-07-17 | 1h | From home to Target is a 15 min drive
2.4 | Pen | Olga Timbur | 3 | 2022-07-17 | 2022-07-17
2.5 | Mouse | Olga Timbur | 0 | 2022-07-17 | 2022-07-17 | N/A | Completed
3 | Class Content |  | 20 | 2022-07-18 | 2022-07-30 | 39h | Complete JavaScript Course 2022
3.1 | JavaScript Fundamentals | Olga Timbur | 0 | 2022-07-18 | 2022-07-20 | 8h | Monday & Tusday From 5-9PM / Wedenesday backup.
3.2 | Developer Skill | Olga Timbur | 0 | 2022-07-21 | 2022-07-21 | 2h | Thursday 5-8 pm
3.3 | JS in the Browser | Olga Timbur | 0 | 2022-07-22 | 2022-07-22 | 4h | Friday 4-7pm breaks are not part og the required time
3.4 | How JS works | Olga Timbur | 0 | 2022-07-23 | 2022-07-23 | 3h | Saturday 9-11 pm
3.5 | Data Structure | Olga Timbur | 0 | 2022-07-23 | 2022-07-23 | 5h | Saturday 1-6 pm
3.6 | Advanced Data Type | Olga Timbur | 0 | 2022-07-25 | 2022-07-26 | 5h | Monday & Tusday From 5-9PM
3.7 | Object Oriented Programming | Olga Timbur | 0 | 2022-07-27 | 2022-07-27 | 4h | Wednesday 5-9 PM
3.8 | Building an Application | Olga Timbur | 0 | 2022-07-28 | 2022-07-30 | 8h | Thurusday 5-7 pm/ Friday 2-5 pm / Saturday 8-12 pm
17 h will be alocated to help on task fallen behind
4 | Class App Required | Olga Timbur | N/A | 2022-07-07 | 2022-07-07 | 30 min | The applications required for the class are installed in the computer.
4.1 | Visual Studio | Olga Timbur | 0 | 2022-07-17 | 2022-07-17 | 30 min | Completed/ 30 min allocated to test the application
4.2 | Chrome | Olga Timbur | 0 | 2022-07-17 | 2022-07-17 | 0 min | Completed
4.3 | notion | Olga Timbur | 0 | 2022-07-17 | 2022-07-17 | 0 min | Completed